## Sheet1
WORK REPORT
Sr. No | Module Name | Part of Module | Assigned By | Work Starts From | Complete On | Time Requried | Completion Status | Testing Starts From | Compted On | Testing Status | Testing Completion Status | Complexity | Extra Description
1 | Student Bulk Upload | Credential Notification | Vedant Patil | 08-11-2016 Afternoon | 08-11-2016 8PM | 1 day | 100% | 2016-11-09 | 9-11-2016 Afternoon | Tested | 80% | Normal | It’s a reworked task.
2 | Student Management | Credential Notification Instantly | Vedant Patil | 9-11-2016 Afternoon | 10/11/2016 3PM | 1 day | 10% |  |  |  |  | Medium | It's sort of going hard for me so it can take some time.